## DailyCall
| Sr. No. | Task Description | External | Owner | Status | Remark
1 | 14 | Project Kick-off | External |  | Completed
2 | 18 | Gather ABHFL/Blazeclan/AWS stakeholders details | External | MG | Completed | Updated Blazeclan, MnM, AWS team details
3 | 19 | Create What's app group | External | ABHFL | Completed
4 | 20 | Daily team meeting | External | ABHFL | Completed | Invite Shared - Daily 10:00AM
5 | 21 | Weekly team meeting | External | MG | Completed | Invite Shared - Every Thursday 2:30 PM
6 | 23 | Team access for Jira, Sharepoint,AWS Management Console | External | MG | Completed
7 | 25 | Decide on IAC tool to implement LZ | External | Anirudh | Completed | Terraform has been finalized as part of SoW
8 |  | Share Landing Zone Questionnaire | External |  | Completed
9 |  | Response on Landing Zone Questionnaire | External |  | Completed
10 | 32 | Direct connect setup for AWS and on-prem connectivity | External |  | Pending | Network Account created and details shared with MnM.
11 |  | VPN setup for AWS and on-prem connectivity | External |  | Pending | Waiting for BGP ASN from MnM
12 |  | Landing Zone Structure Design | External |  | Completed | Created and presented
13 | 54 | Confirmation on proposed Landing zone OU Architecture | External |  | Completed | Received approval for AFT/Security/Infra OU and accounts strucuture. Workload related structure approval is also received. Uploaded the approved staructure on sharepoint
14 | 55 | Creation of Master account | External |  | Completed
15 | 57 | AWS control tower initial setup | External | Anirudh | Completed | AWS Control Tower initial setup completed with Security OU, Infra OU and AFT OU. Security OU has Log and Audit account whereas AFT OU has AFT Management account
16 |  | Region deny configuration | External |  | Completed | Enabled region deny guardrail as part of AWS Control Tower setup
17 |  | AFT Management account setup for Terraform | External |  | Completed
18 | 58 | Network account creation under Infra OU for on-prem to AWS connectivity | External | Anirudh | Completed | Network account created and details are shared
19 | 64 | High Level Design Architecture | External |  | Completed | Discussed on 22nd Nov with Mustan/Abhishek/Jishnu(AWS)
20 |  | High Level Design Architecture Approval | External |  | Completed | HLD discussed with all stake holders and agreed. Uploaded on sharepoint
21 | 65 | Confirmation on IP ranges | External |  | Completed | MnM has received VPC CIDR ranges from their Network team. Abhishek has created the subnets and sheet uploaded on sharepoint
22 | 68 | AWS SSO Permission Sets | External |  | Completed | Policy to attach need to be consider based on the role and least privilege access best practice. Permission Sets recommendation is shared
23 |  | Resource naming and tagging strategy | External |  | Completed | Naming and tagging strategy is finalized, same has been uploaded on sharepoint by MnM
24 |  | Logging | External |  | Completed | Cloudtrail and config logs are aggregated to Log Account and logs are stored in an S3 bucket
25 |  | Monitoring | External |  | Completed | MnM has checked and confirmed with Atul that ELK will be used for monitoring and will be deployed by MnM vendor
26 |  | AWS KMS usage | External |  | Completed | Account wise AWS KMS to be used
27 |  | Security Control (Guardrails) discussion | External |  | Completed | Discussed on 22nd Nov, initially strongly recommended and elective guardrails will be applied on the lowest level OU in the hierarchy
28 |  | Billing and Chargeback Model | External |  | Completed | Account wise billing
29 | 69 | IP subnet discussion - CIDR | External |  | Completed | Subnet requirement details shared with MnM for Landing Zone setup. Abhishek has created subnet CIDRs and uploaded on shrepoint
30 |  | Finalize and approval on the AWS Guardduty and AWS Security Hub | External |  | Pending | Pricing example for both the services is shared
31 |  | Pricing example estimate for AWS Guarduty and AWS Security Hub services. | External |  | Completed | Details shared
32 | 70 | Low Level Design Architecture | External |  | Completed | Created LLDs
33 |  | Low Level Design Architecture Approval | External |  | Completed | All LLD's are discussed and approved
34 |  | Create landing zone design document | External |  | Completed | Prepared and shared draft with MnM
35 | 92 | Review design document with stakeholders | External |  | Pending
36 | 93 | Update design document with feedback | External |  | Pending
37 | 94 | Approval of landing zone design | External |  | Pending
38 | 98 | List of AWS Control tower activities | External
39 |  | AWS IAM Identity Provider (or AWS SSO) integration activity | External |  | Completed
40 |  | Discussion on Firewall | External |  | Completed | MnM is now not using either PaloAlto or AWS Network Firewall which was decided earlier. Zscalar clud connectores are deployed in Central Egress account
41 |  | Routing as per firewall setup | External |  | Completed
42 |  | Centralize Certificate Manager | External |  | Completed | Certificates can be managed account wise only
43 |  | SCP so that no user including users having admin privileges will be able to create VPC’s in AWS accounts which will act as VPC Participant as per the HLD | External |  | Pending | SCP is ready, need to implement
44 |  | Need to have separate Network Account and Appliance Account as separate teams are going to manage them. | External |  | Completed | Updated the HLD
45 |  | Bastion host, Systems Manager, AWS Workspaces will be considered for accessing private instances but this will not be a road blocker for finalizing the HLD | External |  | Pending | MnM has evaluated Cloud9 as well with AWS team. Decision pending with MnM
46 |  | File uploading by developers via S3 or AWS CLI | External
47 |  | AWS Service classification based on Global/Regional/AZ as part of Design Document | External |  | Completed | List Prepared
48 |  | AWS Firewall Manager VPC Security Group Policies to be used | External |  | Completed
49 |  | AWS Network Firewall in-place of 3rd party Security Appliance | External |  | Completed | MnM has decided not to use AWS Network Firewall
50 |  | Dev DMS account | External |  | Completed | Account created and details shared
51 |  | Tag enforcement policy | External

## Plan
Task |  | Status | Remarks
Project Setup
Kick-off with ABHFL Stakeholders | MnM , Blazeclan | Done
Stakeholders Identification | MnM , Blazeclan | Done
Review and Agree on Communication plan, Governance Plan and common tool to be used during the project | MnM , Blazeclan | Done
AWS account access to Blazeclan team | MnM , Blazeclan | Done
Requirement Gathering Workshops
Fill up Landing Zone Questionnaire by MnM team | MnM , Blazeclan | Done
Blazeclan technical team to review the completed Landing Zone Questionnaire Sheet shared by MnM and analyse gaps in information | MnM,Blazeclan | Done
Understand overall IT environment and organization structure |  | Done
Gather requirement from Infra and Network team | MnM , Blazeclan | Done
Understand the network and network security components | MnM , Blazeclan | Done
Gather requirement from security team | MnM , Blazeclan | Done
Understand and capture security, governance and compliance requirement | MnM , Blazeclan | Done
Gather information on IT strategy and billing strategy | MnM , Blazeclan | Done
Understand existing AWS footprint, if any, and discuss future state. | MnM , Blazeclan | Done
AWS landing zone design
Design Landing Zone organization model and account strategy | MnM , Blazeclan | Done
Prepare AWS Control Tower Structure Design | MnM , Blazeclan | Done
Design billing hierarchy and chargeback model | MnM , Blazeclan
Design security baseline for landing zone | MnM , Blazeclan | Done
Define applicable security and compliance guardrails | MnM , Blazeclan | Done
Design network topology and connectivity | MnM , Blazeclan | Done
Design High Level Diagram | MnM , Blazeclan | Done
Design Low level Diagram | MnM , Blazeclan | Done
Approval of HLD and LLD | MnM | Done
Resource naming and tagging strategy | MnM , Blazeclan | Done
Logging and monitoring | MnM , Blazeclan | Done
Finalize and agree on the security tools like AWS Guardduty and AWS Security Hub | MnM , Blazeclan | Done | AWS Guardduty to be used with Audit account as delegated admin. Not using AWS Security Hub
Decide on Landing zone implementation options | MnM , Blazeclan | Done
Review design document with stakeholders (including firewall team) | MnM , Blazeclan | Done | Submitted
Update design document with feedback | MnM , Blazeclan | Done
Submit landing zone design document | MnM , Blazeclan | Done | Submitted
Landing Zone Setup
Setup of AWS Landing Zone as per approved design
Initial Setup of AWS Control Tower | MnM , Blazeclan | Done
Create AFT OU and AFT Management Account for Terraform | MnM , Blazeclan | Done
Create other Ous and accounts as per approved design | MnM , Blazeclan | Done | Corporate OU's and accounts are created. Creating business OUs will be an ongoing process
Integration of AWS IAM Identity Center (or AWS SSO) and Azure AD in Management Account | MnM , Blazeclan | Done
Permission Sets configuration based on least privilege access | MnM , Blazeclan | Pending | Shared recommended Permission Sets. Some permission sets are created
Enforce tagging strategy | MnM , Blazeclan | Done | Discussed with Mustan on 8 Dec'12, MnM has decided to enforce tagging using mPaas tool as per their decision alongwith Karthik. Not required to configure using AWS anymore.
Configure AWS Shared Services Account | MnM , Blazeclan | Done | Dev,UAT and PRD are created and infra provisioned
Configure Log Archive Account | MnM , Blazeclan | Done
Configure Audit Account Account | MnM , Blazeclan | Done
Configure AWS Config | MnM , Blazeclan | Done
Configure CloudTrail | MnM , Blazeclan | Done
Implementing security baseline (Guardrail) | MnM , Blazeclan | Done | Applied on lowest nested OU's which are already created. It will be on ongoing activity for future OUs
Configure CloudWatch | MnM , Blazeclan | Done | ELK is finalized as Monitoring tool and will be setup by MnM vendor
Cost allocation tags setup | MnM , Blazeclan | Done | Cost allocation tags are finalized and will be enforced using mPaas
Setup cloud native Network and Security configuration | MnM , Blazeclan |  | Zscalar Cloud Connector setup is done as part of Networking Configuration.
Configure AWS Guard Duty/Security Hub | MnM , Blazeclan | Done | Configured AWS GuardDuty with Audit account as delegated admin
Configure AWS Key Management Service | MnM , Blazeclan | Done | Account wise AWS KMS will be used
Configure AWS Firewall Manager | MnM , Blazeclan | Done | Configured AWS Firewall Manager with Audit account as delegated admin
VPC Flow Log | MnM , Blazeclan | Pending | Finalized to setup using CFT in AWS Master account using AWS provided solution (https://aws.amazon.com/blogs/mt/vpc-flow-log-with-aws-control-tower-lifecycle/). Getting quota error for lambda while executing the solution. Mail sent to Abhishek to increase the quota value to 1000
Cloudbolt role in each account | MnM , Blazeclan | Done | Done by Abhishek via CFT provided by Cloudbolt team
Breakglass user in each account | MnM , Blazeclan | Pending | Discussed the solution with Abhishek for creating a user in AWS Master account and cross-account role in child accounts. Abhishek will check with Mustan and confirm.
TGW RT creation | MnM , Blazeclan | Done
Assist customer to setup budget alert | MnM , Blazeclan | Done | MnM using Cloudbolt as Finops tool
Network topology and connectivity
Implement network architecture as per design
Setup VPC and subnet for each AWS account | MnM , Blazeclan | Done | Network, CentralEgress, Common Service and Shared Services (dev,uat,prd) completed.
Configure Inter-VPC communication | MnM , Blazeclan | Done | Transit Gateway setup in Network Account. Attachment created in Network,CentralEgress.Common Service and Shared Service accounts(dev,uat,prd).
Support Firewall setup from infra side | MnM , Blazeclan | Done | Zscalar Cloud Connector setup in Central Egress account. Testing is completed
Internal Domain Resolution setup | MnM , Blazeclan | Done | All 4 PHZs are created, resolver rules created and shared in common service account. On-going activity as and when new VPC's come in future.
AWS Private Link Setup | MnM , Blazeclan | Done | PHZs and vpcendpoints are created for ssm, ssm-messages, ec2-messages are created in common service account. Need to test
VPN Setup | MnM , Blazeclan | Done | AWS-Onprem connectivity also tested
Direct Connect | MnM , Blazeclan | Done | Direct Connect configuration done.
Validation of landing zone
Conduct AWS WAR | MnM , Blazeclan | Pending
Test and confirm setup | MnM , Blazeclan | Pending | VPC to VPC communication via TGW, Central internet egress via Zscalar, AWS-OnPrem communication via VPN, PHZs(Internal Domain Resolution), AWS Private Link are tested. AWS-OnPrem connectivity testing via Direct Connect is pending due to pending configuration at on-prem side.
Validate network Infrastrcture | MnM , Blazeclan | Done | VPC to VPC communication via TGW, Central internet egress via Zscalar and AWS-OnPrem communications are tested
Validate policies | MnM , Blazeclan | Done
Handover and Sign off
Handover of project documents to client | MnM , Blazeclan
Project Sign off | MnM , Blazeclan

## LOA
Sr.No | List of Activities for AWS Control Tower (Landing Zone) Setup | Remarks
1 | AWS Master account creation for ABHFL | Done
2 | Enable MFA for root | Done
3 | Admin access for Blazeclan Team on AWS Console | Done
4 | AWS Control Tower setup with default OU's and account | Control tower setup completed in HOME REGION (Mumbai)
5 | Notification sent on emailid's, need to accept | Done
6 | Create AFT OU and AFT Management Account | Done
7 | Configure AFT Management Account for terraform | Done
8 | Creation of additional OU and account as per approved landing Zone design | Pending
9 | Notification sent on emailid's, need to accept
10 | Configure Region Deny GuardRail | Done as part of Control Tower setup
11 | Implement Security Baseline (Enabling Guardrails on OU's/Accounts) | Elective are pending
12 | AWS IAM Identity Center (or AWS SSO) and Azure AD integration in AWS Master Account. | Done
13 | Permission Sets creation in AWS SSO (Master Account) | Shared the list, need to finalize
14 | Enforce tagging strategy | DMS tags sheet will be applicable to other businesses also or they have different tags
15 | Delegate Admin for AWS GuardDuty and AWS Security Hub | Costing sheet shared, need to discuss further
16 | Enable GuardDuty and Security Hub
17 | Configure AWS Cloudtrail and AWS Config on all accounts which send logs to central bucket created in Logging Account | Done as part of Control Tower setup
18 | Configure AWS Key Management Service | As and when required, need to create AWS KMS
19 | Assist customer to setup budget alert | Need to setup in consultation with customer
20 | Implement network architecture as per design
21 | Creation of VPC, Subnet and Route Table in AWS accounts
22 | Creation of Internet Gateway in required accounts
23 | Creation of NAT gateway in Network Account
24 | Creation of Transit Gateway in Network Account
25 | Share Transit Gateway(TGW) of Network account with required OU's accounts
26 | Accept request for shared TGW in all the OU's accounts
27 | Creation of Transit Gateway attachments in required OU's accounts
28 | Create and update transit Gateway route tables in required OU's accounts as per network design
29 | Edit route tables of every created subnet across all accounts as per network design
30 | Direct Connect tasks | Once connection is created by DX partner, need below details: type of virtual interface (public / private / transit); BGP ASN for the vif; VLAN id
31 | VPN tasks | Need Customer Gateway IP address and customer bgp asn
32 | Support Firewall setup from infra side

## Contact
Contact Details
Sr.No. | Name | Designation | Organization | Email ID | Mobile
1 | Ankit Sahai | Solution Architect | Blazeclan | Ankit.Sahai@blazeclan.com | 9168059933
2 | Nayan Rajani | Cloud App Developer (Terraform) | Blazeclan | nayan.rajani@blazeclan.com | 9039143457
3 | BURHANPURWALA MUSTANSIR | Lead Cloud Platform | MnM | BURHANPURWALA.MUSTANSIR@mahindra.com | 9870274428
4 | KAMBLE ABHISHEK |  | MnM | KAMBLE ABHISHEK | 9773571690
5 | Vaidyanathan, Aparajithan | Principal Enterprise Solutions Architect | AWS | aparvaid@amazon.com | 9686938528
6 | Jishnu Dasgupta | Solution Architect | AWS | jdasgpta@amazon.com | 9920702826

## Sheet1
OU | Account Name | Account ID | Email ID | SSOUserEmail
root | Account-LZ2.0-Master | 292929786526 | sukhwal.abhishek@mahindra.com
root->Security | Account-LZ2.0-Audit | 750978287098 | AWSAUDITACC@mahindra.com
root->Security | Account-LZ2.0-Log-Archive | 90548474300 | AWSLOGLOGACC@mahindra.com
root->Infra | Account-LZ2.0-Network | 900089907183 | awsacc_network_prd@mahindra.com | bcone-60194@mahindra.com
root->Infra | Account-LZ2.0-Central-Egress | 428686226277 | awsacc_centreg_prd@mahindra.com | bcone-60194@mahindra.com
root->Infra | Account-LZ2.0-Common-Service | 172547168041 | awsacc_com_prd@mahindra.com | bcone-60194@mahindra.com
root->AFT | Account-LZ2.0-AFT | 802587446688 | AWSAFTACC@mahindra.com
root->AD-OU->SharedService-OU->PRD-OU | Account-LZ2.0-Shared-Prod | 58895454645 | awsacc_shared_prd@mahindra.com | bcone-60194@mahindra.com
root->AD-OU->SharedService-OU->UAT-OU | Account-LZ2.0-Shared-UAT | 335446272886 | awsacc_shared_uat@mahindra.com | bcone-60194@mahindra.com
root->AD-OU->SharedService-OU->DEV-OU | Account-LZ2.0-Shared-Dev | 679578531064 | awsacc_shared_dev@mahindra.com | bcone-60194@mahindra.com
root->AD-OU->DMS2.0-OU->PRD-OU | Account-DMS2.0-PRD | 618710243312 | awsacc_dms2_uat@mahindra.com | bcone-60194@mahindra.com
root->AD-OU->DMS2.0-OU->UAT-OU | Account-DMS2.0-UAT | 460995080542 | awsacc_dms2_prd@mahindra.com | bcone-60194@mahindra.com
root->AD-OU->DMS2.0-OU->DEV-OU | Account-DMS2.0-DEV | 803584912514 | awsacc_dms2_dev@mahindra.com | bcone-60194@mahindra.com
root->MLDL-OU->Metaverse-OU->DEV-OU | Account-meta-dev | 885591765728 | awsacc_meta_dev@mahindra.com | bcone-60194@mahindra.com
root->AD-OU->VES-OU->DEV-OU | Account-bev-dev | 295136033060 | awsacc_bev_dev@mahindra.com | bcone-60194@mahindra.com
root>Sandbox-OU>mPaaS-OU | Account-mpaas-dev | 73311925327 | awsacc_mpaas_dev@mahindra.com | bcone-60194@mahindra.com
| Account Name | Account ID | Email ID
| Account-mpaas-dev | 73311925327 | awsacc_mpaas_dev@mahindra.com

## Sheet2
Policy Name | Description
AmazonEC2FullAccess | Provides full access to Amazon EC2 via the AWS Management Console.
AmazonEC2ReadOnlyAccess | Provides read only access to Amazon EC2 via the AWS Management Console.
AmazonRDSFullAccess | Provides full access to Amazon RDS via the AWS Management Console.
AmazonRDSReadOnlyAccess | Provides read only access to Amazon RDS via the AWS Management Console.
NetworkAdministrator | Grants full access permissions to AWS services and actions required to set up and configure AWS network resources.
AWSNetworkManagerFullAccess | Provides full access to Amazon NetworkManager via the AWS Management Console.
AWSNetworkManagerReadOnlyAccess | Provides read only access to Amazon NetworkManager via the AWS Management Console.
AmazonS3FullAccess | Provides full access to all buckets via the AWS Management Console.
AmazonS3ReadOnlyAccess | Provides read only access to all buckets via the AWS Management Console.
AmazonVPCFullAccess | Provides full access to Amazon VPC via the AWS
AmazonVPCReadOnlyAccess | Provides read only access to Amazon VPC via the AWS Management Console.
SecurityAudit | The security audit template grants access to read security configuration metadata. It is useful for software that audits the configuration of an AWS account.
AWSSecurityHubFullAccess | Provides full access to use AWS Security Hub.
AmazonGuardDutyFullAccess | Provides full access to use Amazon GuardDuty.
AmazonGuardDutyReadOnlyAccess | Provides read only access to Amazon GuardDuty resources
AWSLambda_FullAccess | Grants full access to AWS Lambda service, AWS Lambda console features, and other related AWS services.
AWSLambda_ReadOnlyAccess | Grants read-only access to AWS Lambda service
AmazonEKSClusterPolicy | This policy provides Kubernetes the permissions it requires to manage resources on your behalf. Kubernetes requires Ec2:CreateTags permissions to place identifying information on EC2 resources including but not limited to Instances, Security Groups, and Elastic Network Interfaces.
AmazonEKSWorkerNodePolicy | This policy allows Amazon EKS worker nodes to connect to Amazon EKS Clusters.
AWSBackupFullAccess | This policy is for backup administrators, granting full access to AWS Backup operations, including creating or editing backup plans, assigning AWS resources to backup plans, deleting backups, and restoring backups.
AWSBackupOperatorAccess | This policy grants users permissions to assign AWS resources to backup plans, create on-demand backups, and restore backups. This policy does not allow the user to create or edit backup plans or to delete scheduled backups after they are created.

## Naming
Type | Naming Pattern
Organizational Units | Root
Security
Infra
AFT
AD-OU:
DMS2.0-OU:
DEV-OU
UAT-OU
PRD-OU
SharedService-OU:
DEV-OU
UAT-OU
PRD-OU
MLDL-OU:
DEV-OU
UAT-OU
PRD-OU
Accounts Naming Conventions
Common Projects | Account-LZ2.0-Master
Account-LZ2.0-Audit
Account-LZ2.0-Log-Archive
Account-LZ2.0-Network
Account-LZ2.0-Common-Service
Account-LZ2.0-Central-Egress
Account-LZ2.0-AFT
Application Projects | Account-DMS2.0-DEV
Account-DMS2.0-UAT
Account-DMS2.0-PRD
Account-LZ2.0-Shared-Dev
Account-LZ2.0-Shared-UAT
Account-LZ2.0-Shared-Prod
VPC
Common Projects | vpc-network-mum-001
vpc-inspection-mum-001
vpc-comsrv-mum-001
Application Projects | vpc-prd-shrd-mum-001
vpc-uat-shrd-mum-001
vpc-dev-shrd-mum-001
vpc-dms-prd-mum-001
vpc-dms-uat-mum-001
vpc-dms-dev-mum-001
SUBNET
Common Projects | snt-network-tgwattach-mum-a01
snt-network-tgwattach-mum-b01
snt-inspection-tgwattach-mum-a01
snt-inspection-tgwattach-mum-b01
snt-inspection-fw-mum-a01
snt-inspection-fw-mum-b01
snt-inspection-natgw-mum-a01
snt-inspection-natgw-mum-b01
snt-comsrv-tgwattach-mum-a01
snt-comsrv-tgwattach-mum-b01
snt-comsrv-bastion-mum-a01
snt-comsrv-bastion-mum-b01
sns-comsrv-resolver-mum-a01
sns-comsrv-resolver-mum-a01
sns-comsrv-vpcep-mum-a01
sns-comsrv-vpcep-mum-b01
Application Projects(Shared) | snt-shared-prd-tgwattach-mum-a01
snt-shared-prd-tgwattach-mum-b01
snt-shared-prd-alb-mum-a01
snt-shared-prd-alb-mum-b01
snt-shared-prd-web-mum-a01
snt-shared-prd-web-mum-b01
snt-shared-prd-app-mum-a01
snt-shared-prd-app-mum-b01
snt-shared-prd-db-mum-a01
snt-shared-prd-db-mum-b01
Application Projects(Independent) | snt-dms-prd-tgwattach-mum-a01
snt-dms-prd-tgwattach-mum-b01
snt-dms-prd-lb-mum-a01
snt-dms-prd-lb-mum-b01
snt-dms-prd-web-mum-a01
snt-dms-prd-web-mum-b01
snt-dms-prd-app-mum-a01
snt-dms-prd-app-mum-b01
snt-dms-prd-db-mum-a01
snt-dms-prd-db-mum-b01

## AWSServiceQuota
Quota name | Applied quota value | AWS default quota value | Adjustable
Auto Scaling groups per region | 500 | 500 | Yes
Classic Load Balancers per Auto Scaling group | Not available | 50 | No
Launch configurations per region | 200 | 200 | Yes
Lifecycle hooks per Auto Scaling group | Not available | 50 | No
Scaling policies per Auto Scaling group | Not available | 50 | No
Scheduled actions per Auto Scaling group | Not available | 125 | No
SNS topics per Auto Scaling group | Not available | 10 | No
Step adjustments per step scaling policy | Not available | 20 | No
Target groups per Auto Scaling group | Not available | 50 | No
All Standard (A, C, D, H, I, M, R, T, Z) Spot Instance Requests | 5 | 5 | Yes
AMI sharing | 1000 | 1000 | Yes
AMIs | 50000 | 50000 | Yes
Attachments per transit gateway | 5000 | 5000 | Yes
Attachments per VPC | 5 | 5 | No
EC2-VPC Elastic IPs | 5 | 5 | Yes
Peering attachments per transit gateway | 50 | 50 | Yes
Route Tables per transit gateway | Not available | 20 | Yes
Routes per transit gateway | 10000 | 10000 | Yes
Transit gateways per account | 5 | 5 | Yes
Transit gateways per Direct Connect Gateway | Not available | 3 | No
Virtual private gateways per region | 5 | 5 | Yes
VPN connections per region | 50 | 50 | Yes
Buckets | Not available | 100 | Yes
Bucket policy | Not available | 20 kilobytes | No
Object size | Not available | 5 terabytes | No
DB instances | 20 | 40 | Yes
DB clusters | 40 | 40 | Yes
Read replicas per master | 15 | 15 | Yes
Total storage for all DB instances | 100,000 gigabytes | 100,000 gigabytes | Yes
Number of groups supported in IAM Identity Center | Not available | 100000 | No
Number of permission sets allowed in IAM Identity Center | Not available | 2000 | Yes
Number of permission sets allowed per AWS account | Not available | 50 | Yes
Number of users supported in IAM Identity Center | Not available | 100000 | Yes
Total number of AWS accounts or applications that can be configured | Not available | 3000 | Yes
ACM certificates | Not available | 2500 | Yes
ACM certificates created in last 365 days | Not available | 5000 | Yes
Domain names per ACM certificate | Not available | 10 | Yes
Imported certificates | Not available | 2500 | Yes
Imported certificates in last 365 days | Not available | 5000 | Yes
Application Load Balancers per Region | 50 | 50 | Yes
Certificates per Application Load Balancer | 25 | 25 | Yes
Classic Load Balancers per Region | 20 | 20 | Yes
Listeners per Application Load Balancer | 50 | 50 | Yes
Network Load Balancers per Region | 50 | 50 | Yes
Targets per Application Load Balancer | 1000 | 1000 | Yes
Clusters | 100 | 100 | Yes
Control plane security groups per cluster | 4 | 4 | No
Fargate profiles per cluster | 10 | 10 | Yes
Label pairs per Fargate profile selector | 5 | 5 | Yes
Managed node groups per cluster | 30 | 30 | Yes
Nodes per managed node group | 450 | 450 | Yes
Public endpoint access CIDR ranges per cluster | 40 | 40 | No
Registered clusters | 10 | 10 | Yes
Selectors per Fargate profile | 5 | 5 | Yes
CompleteSnapshot requests per account | 10 per second | 10 per second | No

## Quota-AWSOrganization
Number of AWS accounts in an organization | 10 — The default maximum number of accounts allowed in an organization. If you need more, you can request an increase by using the Service Quotas console.
An invitation sent to an account counts against this quota. The count is returned if the invited account declines, the management account cancels the invitation, or the invitation expires.
Number of roots in an organization | 1
Number of OUs in an organization | 1000
Number of policies of each type in an organization | 1000 per policy type
Maximum size of a policy document | Service control policies: 5120 bytes (not characters)
AI services opt-out policies: 2500 characters
Backup policies: 10,000 characters
Tag policies: 10,000 characters
Note: If you save the policy by using the AWS Management Console, extra white space (such as spaces and line breaks) between JSON elements and outside of quotation marks, is removed and not counted. If you save the policy using an SDK operation or the AWS CLI, then the policy is saved exactly as you provided and no automatic removal of characters occurs.
OU maximum nesting in a root | Five levels of OUs deep under a root.
Maximum number of invitation attempts you can perform in a 24-hour period | Either 20 or the maximum number of accounts allowed in your organization, whichever is greater. Accepted invitations don't count against this quota. As soon as one invitation is accepted, you can send another invitation that same day.
If the maximum number of accounts allowed in your organization is less than 20, then you get an "account limit exceeded" exception if you attempt to invite more accounts than your organization can contain. However, you can cancel invitations and send new ones up to the maximum of 20 attempts in one day.
Number of member accounts you can create concurrently | 5 — As soon as one finishes, you can start another, but only five can be in progress at a time.
Number of member accounts you can close in a 30 day period | 10% of active member accounts in an organization can be closed within a 30 day period. The maximum account closure is 200, even if 10% active accounts exceeds 200.
Number of member accounts you can close concurrently | 3 — Only three account closures can be in progress at the same time. As soon as one finishes, you can close another account.
Number of entities to which you can attach a policy | Unlimited
Number of tags that you can attach to a root, OU, or account | 50

## Egress
| AWS Account Name | VPC | Subnet | Route Table | NAT Gateway | Internet Gateway | Gateway LB | Gateway LB Endpoint Service | Gateway LB Endpoint | EC2 | TGW Attachment
1 | Account-LZ2.0-Central-Egress
|  | vpc-0e4b0f0d8d05233b5 / vpc-inspection-mum-001 10.167.0.0/20 |  |  |  | igw-0ae5465a320f4dae6 / igw-inspection-mum-01 | zsdemo-cc-gwlb-tt36kjcg | vpce-svc-0f583fd2b3906b991 / zsdemo-cc-gwlb-vpce-service-tt36kjcg | vpce-086e042cdd70c92a5 / zsdemo-client-vpce-az2-tt36kjcg |  | tgw-attach-02da354dbec0edcaf / tgw-inspection-tgwattach-mum-01
|  |  | subnet-047fdc5ef2147f622 / snt-inspection-tgwattach-mum-a01 10.167.0.0/28 | rtb-093a341e50cdf872c / rtb-inspection-tgwattach-mum-a01 |  |  |  |  | vpce-0b86e7856fe022821 / zsdemo-client-vpce-az1-tt36kjcg
|  |  | subnet-07a038d159d47a060 / snt-inspection-tgwattach-mum-b01 10.167.0.16/28 | rtb-08b2c36b878a1d008 / rtb-inspection-tgwattach-mum-b01
|  |  | subnet-08f47bbed8bbb0024 / snt-inspection-fw-mum-a01 10.167.0.32/28 | rtb-023529b261310e25c / zsdemo-cc-rt-ngw-2-tt36kjcg | [5 empty] | i-0bdfc996aeec3ce28 (zsdemo-cc-vm-2-tt36kjcg)
|  |  | subnet-0fe6a666c94e1bd7d / snt-inspection-fw-mum-b01 10.167.0.48/28 | rtb-079dec466c566980e / zsdemo-cc-rt-ngw-1-tt36kjcg | [5 empty] | i-02ad5c2be0e8a1efb (zsdemo-cc-vm-1-tt36kjcg)
|  |  | subnet-09e5b99655d0ec20b / snt-inspection-natgw-mum-a01 10.167.0.64/28 | rtb-0d94c0700ca2d646d / rtb-inspection-natgw-mum-a01 | nat-08331312bf1396e89
|  |  | subnet-0a6e9d1297b3ca7ac / snt-inspection-natgw-mum-b01 10.167.0.80/28 | rtb-03f95782f28c08404 / rtb-inspection-natgw-mum-b01 | nat-0c370950a1880c479

## Network
S.No. | AWS Account Name | VPC | Subnet | Route Table | Transit Gateway | TGW Attachment | TGW RoutTable | Customer Gateway | VPN Connections
1 | Account-LZ2.0-Network
|  | vpc-072d6c518854f2ed6 / vpc-network-mum-001 |  |  | tgw-054cb211a3fa7db6e / tgw-network-mum-01 | tgw-attach-09028eb16ea094d3a / tgw-network-tgwattach-mum-01 | tgw-rtb-0169c90368599c110 / tgw-network-mum-01 | cgw-02e46db29f311cafa / mm_cgw_mrv | vpn-01f2f7eaffaec1d9d / mm-s2s-mrv
|  |  | subnet-01afb6f3165fe714b / snt-network-tgwattach-mum-a01 | rtb-00c842c3628d30b5e / rtb-network-private-mum-a01 |  |  | tgw-rtb-0565cd127f48b5e97 / tgwrtb-network-vpn-mum-01 | cgw-041c95731b15f2299 / mm_cgw_mitc | vpn-009dcda5c91896c0c / mm-s2s-mitc
|  |  | subnet-0f5ffd46f7c6f443c / snt-network-tgwattach-mum-b01 | rtb-02039de2d5d697147 / rtb-network-private-mum-b01

## InfraCreation-Status
Account Name | Task | Remarks
Account-LZ2.0-Master
| AWS Control Tower Setup | Completed with Mumbai as region
| OU's | Corporate OU's i.e Security, Infra, AFT are created. Some Business related OU's are also created as per the requirement. It will be an ongoing process
| Accounts | Corporate accounts like Audit, Logging, Network, Central Egress, Common Service, AFT Management are created. Business related accounts are also created as per the requirement. It will be an ongoing process
| Guardrails | Mandatory will be automatically applied at root OU which will be ihereted by all OU's and accounts. Strongly Recommended and Elective are applied on lowest level of existing nested OU's. It will be an ongoing activity
| AWS SSO | AWS Identity Provider is integrated with Azure AD
| AWS SSO Permission Sets | Currently defaults are used. Need to create more as per the requirement
| Tagging Policy | Not to implement as tagging will be enforced at mPAAS tool
| Delegate Audit account as admin for AWS Firewall Manager | Completed
| SCP to deny VPC & Subnet creation on Participany VPC's accounts | Completed. Created the scp and applied on VES-OU - > DEV-OU
Account-LZ2.0-Network
| VPC | 1
| Subnets | 1 each in AZ (a and b)
| Route Table | Need to update routes as per the requirement
| Transit Gateway(TGW) | 1 in Mumbai region
| TGW Attachment | 1
| TGW Shared using RAM | Shared with Central Egress Account. Ongoing activity as per requirement and new VPC provisioning
| TGW Route Table | 2 RT's are created. Need to add routes as per the rqequirement
| VPN | Completed. VPN tunnel is UP and testing successfully done.
| Direct Connect | Completed.
| Modified TGW RT | Completed
Account-LZ2.0-Central-Egress
| VPC | 1
| Subnets | 3 in each AZ (a nd b)
| Route Table | Individual RT for each subnet. Routes added
| TGW Attachment | 1
| Gateway Loadbalancer | 1
| GW Loadbalancer Service Endpoint | 1
| GW Loadbalancer Endpoints | 2 (1 in each Inspection Subnet)
| NAT Gateway | 1 in each NAT GW Subnet
| Internet Gateway | 1
| Zscalar Cloud Connector | 1 ec2 instance in each Inspection subnet
| Testing | Done
| NAT GW Subnet RT entry | Pending. All VPC's CIDR which will point to GWLBEP
Account-LZ2.0-Common-Service
| VPC | 1
| Subnets | 4 in each AZ (a and b)
| Route Table | 4
| TGW Attachment | 1
| Route53 PHZ | 4(shared,dev,uat,prd) and 3(ssm,ssm-messages,ec2-messages vpcendpoints)
| Route53 Outbound Resolver | 2
| Route53 Inbound Resolver | 1
Association with workload VPC's
| Resolver Rules | 2
| Share Resolver Rules with workload VPC's | Shared Services accounts
Bastion Host
| VPC Endpoints | 3 (ssm, ssm-messages,ec2-messages)
Account-LZ2.0-Log-Archive
| S3 bucket | Cloudtrail and AWS Config logs are aggregated in this bucket as part of AWS Control Tower setup
Account-LZ2.0-Audit
| AWS Guardduty | Completed
| AWS Securtity Hub | MnM confirmed not to implement it.
| AWS Firewall Manager | Completed
Account-LZ2.0-Shared-Prod | VPC | 1
| Subnets | 5 in each AZ (a nd b)
| Route Table | 5
| TGW Attachment | 1
| Internet gateway | 1
| Subnet Routing | Done
| Share Subnet | Done as per requirement. On-going activity
Account-LZ2.0-Shared-UAT | VPC | 1
| Subnets | 5 in each AZ (a nd b)
| Route Table | 5
| TGW Attachment | 1
| Internet gateway | 1
| Subnet Routing | Done
| Share Subnet | Done as per requirement. On-going activity
Account-LZ2.0-Shared-Dev | VPC | 1
| Subnets | 5 in each AZ (a nd b)
| Route Table | 5
| TGW Attachment | 1
| Internet gateway | 1
| Subnet Routing | Done
| Share Subnet | Done as per requirement. On-going activity
For All Accounts | Routing | Routing to be done in each and every account as per the requirement