## Milestone Plan
Phases ¦ Milestones ¦ Activities | Wk1 | Wk2 | WK3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8
Project Setup | bar: Wk1
Requirement Gathering | bar: Wk1 to Wk2
Landing Zone Design and strategy | bar: Wk2 to WK3
AWS Control Tower setup | bar: Wk2 to Wk4
Implement network architecture | bar: Wk5 to Wk7
Validation of Landing zone | bar: Wk6 to Wk8
Handover and Signoff | bar: Wk8

## Project Plan (2)
SN | Phases | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Project Setup
1 | Stakeholder identification
2 | Develop a detailed project plan
3 | Access to AWS environment to Blazeclan team
Requirement Gathering Workshops
4 | Understand overall IT environment and organization structure
5 | Gather requirement from Infra and Network team
6 | Understand the network and network security components
7 | Gather requirement from security team
8 | Understand and capture security, governance and compliance requirement
9 | Gather information on IT strategy and billing strategy
10 | Understand existing AWS footprint, if any, and discuss future state.
AWS landing zone design
11 | Design Landing Zone organization model and account strategy
12 | Design billing hierarchy and chargeback model
13 | Design security baseline for landing zone
14 | Define applicable security and compliance guardrails
15 | Design identity and access management solution
16 | Design network topology and connectivity
17 | Low level VPC/Subnet design
18 | Resource naming and tagging strategy
19 | Logging and monitoring
20 | Decide on Landing zone implementation options
21 | Create landing zone design document
22 | Review design document with stakeholders (including firewall team)
23 | Update design document with feedback
24 | Approval of landing zone design
AWS landing zone setup
25 | Setup of AWS Landing Zone as per approved design
26 | Implement multi-account strategy for landing zone
29 | AWS SSO and Azure AD Integration
30 | IAM Policies configuration/Configure IAM based on least privilege access
31 | Enforce tagging strategy
32 | Configure log archive account
33 | Configure security account
34 | Monitoring and logging strategy
35 | Implementing security baseline (Guardrail)
36 | Setup cloud native network and security configuration
37 | Configure AWS config rule and configure AWS SNS
38 | Configure AWS Guard Duty/Security Hub
39 | Configure AWS Key Management Service
40 | Cost allocation tags setup
41 | Assist customer to setup budget alert
Network topology and connectivity
42 | Implement network architecture as per design
43 | Setup VPC and subnet for each AWS account
44 | Configure Inter-VPC communication
45 | Support Firewall setup from infra side
Validation of landing zone
46 | Conduct AWS WAR
47 | Test and confirm setup
48 | Validate network Infrastrcture
49 | Validate policies
Handover and Sign off
50 | Handover of project documents to client
51 | Project Sign off

## Project Plan
SN | Phases | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
Project Setup
1 | Stakeholder identification
2 | Develop a detailed project plan
3 | Access to AWS environment to Blazeclan team
Requirement Gathering Workshops
4 | Understand overall IT environment and organization structure
5 | Gather requirement from Infra and Network team
6 | Understand the network and network security components
7 | Gather requirement from security team
8 | Understand and capture security, governance and compliance requirement
9 | Gather information on IT strategy and billing strategy
10 | Understand existing AWS footprint, if any, and discuss future state.
AWS landing zone design
11 | Design Landing Zone organization model and account strategy
12 | Design billing hierarchy and chargeback model
13 | Design security baseline for landing zone
14 | Define applicable security and compliance guardrails
15 | Design identity and access management solution
16 | Design network topology and connectivity
17 | Low level VPC/Subnet design
18 | Resource naming and tagging strategy
19 | Logging and monitoring
20 | Decide on Landing zone implementation options
21 | Create landing zone design document
22 | Review design document with stakeholders (including firewall team)
23 | Update design document with feedback
24 | Approval of landing zone design
AWS landing zone setup
25 | Setup of AWS Landing Zone as per approved design
26 | Implement multi-account strategy for landing zone
29 | AWS SSO and Azure AD Integration
30 | IAM Policies configuration/Configure IAM based on least privilege access
31 | Enforce tagging strategy
32 | Configure log archive account
33 | Configure security account
34 | Monitoring and logging strategy
35 | Implementing security baseline (Guardrail)
36 | Setup cloud native network and security configuration
37 | Configure AWS config rule and configure AWS SNS
38 | Configure AWS Guard Duty/Security Hub
39 | Configure AWS Key Management Service
40 | Cost allocation tags setup
41 | Assist customer to setup budget alert
Network topology and connectivity
42 | Implement network architecture as per design
43 | Setup VPC and subnet for each AWS account
44 | Configure Inter-VPC communication
45 | Support Firewall setup from infra side
Validation of landing zone
46 | Conduct AWS WAR
47 | Test and confirm setup
48 | Validate network Infrastrcture
49 | Validate policies
Handover and Sign off
50 | Handover of project documents to client
51 | Project Sign off

## WeeklyTask
2022-11-17
Activities Completed Last Week | Ongoing Activities This Week | Upcoming Activities For Next Week
AWS Control Tower Structure Design
AWS Control Tower Initial Set-up
Discussed AFT functionality
AWS SSO - Azure AD Integration
2022-11-24
Activities Completed Last Week | Ongoing Activities This Week | Upcoming Activities For Next Week
AWS Control Tower Structure Design | AWS Control Tower strucutre design is approved | Approval on HLD
AWS Control Tower Initial Set-up | AWS AFT Management account setup is done | Prepare LLD
Discussed AFT functionality | Network and DMS dev accounts creation | Prepare Design Document
AWS SSO - Azure AD Integration | Enable KMS enccryption in Control Tower setting | On-prem to AWS connectivity using Direct Connect
Log configuration for Amazon S3 Bucket retention is completed in AWS Control Tower settings
Resource naming convention and tagging has been finalized and agreed to use the same as in other cloud platforms of MnM
Guardrails discussion and finalized to apply all guardrails on each of the lowest OU in hierarchy
AWS KMS Customer Managed Keys (CMK) will be used in individual AWS accounts
Finalized to use AWS Firewall Manager VPC Security Group Policies
Finalized to use ELK for monitoring instead of AWS CloudWatch and will be deployed by MnM vendor
2022-12-01
Activities Completed Last Week | Ongoing Activities This Week | Upcoming Activities For Next Week
AWS Control Tower strucutre design is approved | Presented and discussed HLD to all stakeholders. All stakeholders agreed on presented HLD | Share Landing Zone Design Document
Created Network and DMS dev accounts | Prepare and share Subnet netmask requirement for Landing Zone infra subnets | Landing Zone setup activities as per HLD
Enabled KMS enccryption in Control Tower setting | Prepare AWS SSO Permission Set use cases
Log configuration for Amazon S3 Bucket retention is completed in AWS Control Tower settings | Pricing example estimate for AWS GuardDuty and AWS Security Hub services
Discussed Guardrails and finalized to apply all guardrails on each of the lowest OU in hierarchy | UAT and Prod DMS account with required OU’s has been created as per the approved AWS Control Tower OU Structure.
AWS KMS Customer Managed Keys (CMK) will be used in individual AWS accounts | Prepare LLD
Finalized to use AWS Firewall Manager VPC Security Group Policies | Prepare Design Document
Finalized to use ELK for monitoring instead of AWS CloudWatch and will be deployed by MnM vendor | Strongly recommended Guardrails are applied on MDS Dev, UAT, Prod Ous
Discussion on ACM and finalized that Certificates has to be managed account wise only
2022-12-08
Activities Completed Last Week | Ongoing Activities This Week | Upcoming Activities For Next Week
Presented and discussed HLD to all stakeholders which includes Mahindra's SOC,NOC, CCoE teams and AWS. All stakeholders agreed on presented HLD | Present and disscuss LLDs for approval with stakeholders which includes Mahindra's CCoE and AWS team | Share Landing Zone Design Document
Prepare and share Subnet netmask requirement for Landing Zone infra subnets | Provision Central Egress and Common Service accounts as per AWS organizational account structure | Perform remaining Landing Zone setup activities as per approved design
Prepare AWS SSO Permission Set use cases | MnM has finalized that Zscalar Cloud Connector will be used as reverse proxy in Central-Egress account in place of Palo-Alto firewall and AWS Network Firewall.
Pricing example estimate for AWS GuardDuty and AWS Security Hub services | Infra provisioning in Central Egress account as per approved architecture for Centralize egress traffic
UAT and Prod DMS account with required OU’s has been created as per the approved AWS Control Tower OU Structure. | Provision Static site-to-site VPN for both On-prem datacentre (MITC & MRV)
Prepare LLD | Transit Gateway provisioning in Network Account
Prepare Design Document
Strongly recommended Guardrails are applied on DMS Dev, UAT, Prod OUs
Discussion on ACM and finalized that Certificates has to be managed account wise only
2022-12-15
Activities Completed Last Week | Ongoing Activities This Week | Upcoming Activities For Next Week
VPC to VPC connectivity testing | Updates and closed the points raised in Design Document | Vallidation and testing of Landing Zone setup
AWS to ONPrem Connectivity testing | Creation of PHZs in Common-Service account for Internal Domain Resolution and AWS Private Link | Conduct AWS WAR
Egress internet traffic through central egress account via zscalar cloud connectors testing | Creation of Inbound and Outbound resolver in Common-Service account
Audit account as delegated admin for AWS Firewall Service | Create Resolver Rules in Common-Service account
SCP to restrict VPC & Subnet creation in VPC Participant account and apply to lowest nested OU in the hierarchy i.e.AD-OU -> VES-OU - > DEV-OU (ou-n3ro-tfni3a0w) | Create AWS account Account-mpaas-dev
Create Shared Service DEV/UAT/PRD accounts | Create accounts Account-electreefi-dev and Account-electreefi-prd and subnets are shared with them from Account-LZ2.0-Shared-Dev & Account-LZ2.0-Shared-Prod respectively
Share subnets with AWS Account Account-bev-dev from Account-Shared-DEV | Direct Connect configuration in Network Account
Submit and discuss draft Landing Zone Design Document | Transit Gateway Route Table creation and modification as per the requirement
Audit account as delegated administrator for AWS GuardDuty

## IssueRisk
Issue/Risk | Date | Description | Priority | Impact | Owner | Response | Status | Resolution Date | Delayed by Days
1 |  | Need to freeze HLD | High | Timelines will get impacted | MnM/Blazeclan |  | Closed | 2022-11-29
2 |  | Need to freeze LLD | High | Timelines will get impacted | MnM/Blazeclan |  | Closed | 2022-12-07 | 4
3 |  | VPN Connectivity | High | Network architecture setup will get delayed | MnM/Blazeclan | AWS Side VPN configuration completed and details shared. On-prem side configuration is pending | Closed | 2022-12-14 | 4
4 |  | Direct Connect Connectivity | High | Network architecture setup will get delayed | MnM/Blazeclan | Network account was created and details shared on 18th Nov'22. Waiting for response from Direct Connect provider | Open
5 |  | Landing Zone Setup | High | Overall project timelines will be impacted | MnM/Blazeclan | Due to delay in freezing the LLDs and receiving required information for common service account setup, landing zone setup activities gets delayed | Closed | 2022-12-21 | 8
6 |  | Landing Zone Design Document Closure | High | Overall project timelines will be impacted | MnM/Blazeclan |  | Open

## Decision
# | Description | Request Date | Close Date | Status | Comments
1 | DMS2.0 will be provisioned with AFT |  |  | Closed | Finalized as per SoW
2 | Firewall team should be included in design phase so we have network design which can be implemented by Palo Alto team |  |  | Closed | MnM team will schedule call with network and security team for HLD dicussion
3 | AWS Control Tower OU Structure | 2022-11-16 | 2022-11-23 | Closed | Approval received
4 | Naming convention and tagging | 2022-11-22 | 2022-11-23 | Closed | Finalized to use existing naming convention and tagging as in other MnM cloud environments
5 | Monitoring tool | 2022-11-22 | 2022-11-23 | Closed | Finalized that MnM will use ELK instead of AWS Cloudwatch and will be setup by ther vendor
6 | HLD finalization | 2022-11-22 | 2022-11-29 | Closed | Presented and discussed with all stakeholders which includes Mahindra's SOC, NOC & CCoE teams, and AWS and agreed upon
7 | Guardrails implementation | 2022-11-22 | 2022-11-23 | Closed | Initially all Guardrails need to apply on lowest nested OU in the Hierarchy
8 | AWS KMS | 2022-11-22 | 2022-11-23 | Closed | Finalized to use AWS CMK KMS on account wise
9 | AWS Certificate Manager | 2022-11-22 | 2022-11-23 | Closed | ACM are scope to region per account
10 | AWS Firewall Manager | 2022-11-22 | 2022-11-23 | Closed | AWS Firewall Manager VPC security groups to be used centrally with Audit account as delegated admin
11 | Instead of Palo Alto Firewall, AWS Network Firewall or some other reverse proxy hosted on ec2 will be used | 2011-11-26 | 2022-12-02 | Closed | MnM has finalized that Zscalar Cloud Connector will be used as reverse proxy in Central-Egress account in place of Palo-Alto firewall and AWS Network Firewall.
12 | LLD Finalization | 2011-11-30 | 2022-12-07 | Closed | Presented and discussed with all stakeholders, which includes Mahindra's CCoE team & AWS team, and agreed upon
13 | AWS Guardduty |  | 2022-12-16 | Closed | AWS Guardduty to be enable with Audit as delegated admin
14 | VPC Flow logs |  | 2022-12-16 | Closed | Enable VPC flow logs and redirect logs to centralize S3 bucket in Log account using AWS provided CFT and setup to be done in AWS Master Account

## MilestoneStatus
Milestone | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Remarks
Project Setup | 2022-11-14 | 2022-11-18 | 2022-11-14 | 2022-11-14 | Completed | Received WVD, Sharepoint and Jira access
Requirement Gathering | 2022-11-14 | 2022-11-25 | 2022-11-14 | 2022-11-25 | Completed | Discussion in progress to finalize on requirement to freeze HLD design
Landing Zone Design and strategy | 2022-11-28 | 2022-12-02 | 2022-11-28 | 2022-12-07 | Completed | HLD & LLDs are freezed.
AWS Control Tower setup | 2022-12-05 | 2022-12-09 | 2022-12-05 | 2022-12-07 | Completed | AWS Control Setup is implemented
Implement network architecture | 2022-12-05 | 2022-12-09 | 2022-12-05 | 2022-12-21 | Completed | Delayed due to delay in LLD approval and other details required for configration
Validation of Landing zone | 2022-12-12 | 2022-12-30 | 2022-12-12 |  | In-Progress | VPC-VPC Connectivity testing via Transit Gateway, Egress Internet via Cloud Connectors in Central Egress account, and OnPrem-AWS Connectivity testing via VPN & TGW are done
Handover and Signoff | 2023-01-02 | 2023-01-06

## Questions
Questions during calls | Owner | Response
Current biller for AWS CT Management account is Tech M. Is there any impact in case biller got changed. | Ankit | As confirmed by Abhishek K(M&M), the root account details belongs to M&M only. Based on this we confirm that in future if biller gets changed then also there will be no impact on AWS CT Management account. Same has been confirmed by Aparajithan Vaidyanathan (AWS) in daily standup call on 17-11-22
Rename Shared Account to Common Account in AWS CT structure | Ankit | Done
Direct Connect speed limitation | AWS | Answered by Aparajithan Vaidyanathan (AWS) over mail
Same emailid can be re-used for new AWS accounts creation | Ankit | We have to use unique emailid for creating new aws accounts
AWS Concurrency limitation mentioned in AWS CT structure diagram | Ankit | Updated the same in diagram
Is it possible to use Programmatic access of one user across all aws accounts | Ankit | Programmatic access details for same SSO user are different for different accounts.
Is it possible to disable to disable IAM in individual accounts | Ankit | In Control Tower setup, AWS SSO use to create cross-account roles in members accounts as part of central login mechanism so we can't disable IAM in aws accounts. We can create permission sets and do not assign IAM permissions to it based on the user role.
AWS Control Tower Structure Design approval | Mustan | Core, Infra and Shared Service OU structure is approved. Following up with mPaaS tool team for LOB specific OU structure
Can guardrails be applied to Nested OU isntead of it's Parent OU | Ankit | We can apply non-mandatory guardrails on nested OU itself instead of it's parent OU, which will be inherited by underlying nested OU and accounts
Can a guardrail be filtered on a child OU that has been propogated from parent OU | Ankit | Policy applied on the Parent OU will be inherited by child OU and can't be excluded

## Sheet3
Sr.No | List of Activities for AWS Infra Creation | Remarks | DATE
1 | AWS Master account creation | Done
2 | Enable MFA for root | Done
3 | AWS Control Tower setup with default OU's and account
4 | Notification sent on emailid's, need to accept
5 | Creation of additional OU and account as per approved landing Zone design
6 | Notification sent on emailid's, need to accept
7 | Enable Region Deny Control
8 | Implementing security baseline (Guardrail)
9 | AWS SSO and Azure AD Integration in AWS Master Account.
10 | Permission Sets creation in AWS SSO (Master Account) based on least privilege access
11 | Delegate Admin for GuardDuty and Security Hub
12 | Enable GuardDuty and Security Hub
13 | Creation of VPC, Subnet and Route Table in AWS accounts
14 | Creation of Internet Gateway in Network Account
15 | Enable VPC flow logs which send logs to central bucket created in Logging Account
16 | Creation of NAT gateway in Network Account
17 | Creation of Transit Gateway (TGW) in Network Account
18 | Share Transit Gateway with other accounts
19 | Accept request for shared TGW2 as per above step(26) in all the ABHFL OU accounts
20 | Creation of Transit Gateway attchments in all VPC's of AWS accounts
21 | Create transit Gateway route tables
22 | Edit route tables of every subnet in all Accounts
23 | Provide support for Firewall setup in Network Account
24 | Delegate Admin (Security Account) for AWS Inspector
25 | Enable AWS Inspector
26 | Configure AWS Key Management Service
27 | Cost allocation tags setup
28 | Assist customer to setup budget alert